## Slide 1: PowerCLI vCommunity Resources used to Migrate to VCSA 6.5u1
Slide said to put something here while I introduced myself.
Notes: Intro
Title: vSphere 6.5u1 migration project – Synacor (this is public info)

## Slide 2: All the things to VCSA!
Goals
  Live migration for minimal VM downtime
  Feature parity across our Empire
    New abilities (Encryption/Containers (VIC)/HA Orchestrated Restart!)
    Simpler SSO roles & permissions (no more local Windows users)
    Active Directory login ability
  Decrease non-VMware troubleshooting/time-sinks
    No more Windows/external Oracle DBs/MS SQL/
  Remove tech-debt
    configs/versions/settings/vm portgroups/certs – standardized
  HTML5 Client
    Our SysAdmins mostly use Non-Windows machines
Notes:     * Minor downtime might be needed for smaller DCs w/less than 4 ESXi Hosts

## Slide 3
5.1b
Win2k8
Physical
DB
5.1b
Win2k8
Physical
DB
Physical DB
Physical DB
5.5c
Win2k8
5.1u3
Win2k8
5.5u3b
vcsa
embedded DB
ESX 4.0
Win2k3
Physical
DB
5.1u3
Win2k8
Physical
DB
Legacy
Install Base
Where we were
(Sites boxed as appropriate)
Physical
DB
5.0GA
5.0u1
Win2k8
Physical
DB
Physical
HyperV!
Notes: New clients were brought onboard, new datacenters opened up, new VMware licenses were purchased for newer versions.
Total SAN = ~4.5 Petabytes (NetApp NFS/FC) (raw)
Total VMs = ~4500 (95% CentOS 5/6)
Total Hosts = ~200
Hardware is the simplest part – all hosts are HP - DL360/BL460 - G6/7/8/9 - dual socket
Notice #5?
A Preprod vCenter was named vc.preprod.local.
It was a VM, in Hyper-V, on physical server named vc01.preprod.local.
Yeah…this is one of those things that was running for ~3 years without anyone knowing this.
There was a reason though.
A project that fell off, and was forgotten about.
At the time, auto-deploy required you to be on a windows domain.

## Slide 4: Where we are now (don’t laugh…well, I do, so go ahead!)
vCenters & Hosts
1 - A1 (prod) - 5.1u3 - win2k8-virtual | ora-physical | domain creds
2 - A2 (dev) - 5.5u3b - vcsa/emb | domain creds
3 - B1 (debt/decom) - 5.5c - win2k8-virtual | ora-physical | domain creds
4 - C1 (prod) - 5.0u1 - win2k8-physical | ora-physical | local creds
5 - C2 (preprod) - 5.0GA - vCenter vm in HYPER-V! | ora-physical | preprod creds
6 - D1 (debt/decom) - 5.1b - win2k8-virtual | ora-physical | local creds
7 - D2 (debt/decom) - 4.0 - ESX - win2k-physical | ora-physical | local creds
8 - Z1 (prod) - 4.0 - ESX - win2k-physical | ora-physical | local creds
9 - Y1 (prod/moving to own) - 5.5u3b - hosts currently connected to B1

## Slide 5: Deployment Topology (Sites boxed as appropriate)
vc-02
psc-05
vc-04
psc-03
psc-01
psc-09
psc-08
vc-07
vc-06
vc-01
vc-09
vc-08
psc-07
psc-06
vc-05
psc-04
vc-03
psc-02
6.5u1
SSO Domain
(vsphere.local)
Enhanced Linked Mode
Notes: There are many different deployment options/topologies that are slightly different between 5.5/6/0/6.5.
I’ve found that if you don’t have a complex VMware Software Solution setup, then adhering to “each vCenter gets an external PSC,” you should be ok.
You can do fancy load-balancing stuff, but you’ll STILL have to manually switch PSCs if you lose one.
We deployed 6.5u1.
We wanted ELM.
It required External PSCs.
It was supported topology.

## Slide 6: How to get there?
Process
  EXPORT EVERYTHING
    (s)DRS Rules, Network Info, VM Folders, Permissions (if necessary)
  NETWORKING
    dvSwitch to vSwitch
    vmkernels/Port Groups
    Move VM Networks
  MOVE HOSTS
    Disconnect the ESXi Hosts from the old vCenter.
    Reconnect the ESXi Hosts to the new vCenter.
  UPDATE ESXi
    Use PowerCLI as VUM won’t be available
Notes: Export Notes:
Export EVERYTHING from your old vCenter (RVTools is very handy here!)
Export EVERYTHING ELSE - (s)DRS Rules, VM Folders, Permissions (if necessary)
Export dvSwitch(es) PortGroups into a CSV
Networking Notes/Order:
Create Standard vSwitch(es) on each Host.
Read in PortGoups and create them on each vSwitch. Choose a slightly different name. Mig-name is what I used.
Create PortGroups on vSwitch on each Host that will be your VMKernels (VLANs).
Disconnect x NICs from dvSwitch. I only did half of mine at a time, just in case.
Use Add-VirtualSwitchPhysicalNetworkAdapter. This moves VMNICs over and can turn a Portgroup into a VMKernel.
Change the PortGroup of the VMs from dvPortGroup to the new temporary PortGroups. Remember to do all of the VMs Adapters.
Move the rest of the VMNICs over.
Remove the Host from the dvSwitch.
MOVE HOSTS
Disconnect the ESX Host from the old vCenter.
Add ESX Host to new vCenter. Add it to the Datacenter, not a Cluster.
Move Host to proper Cluster.

## Slide 7: How to get there?
Export EVERYTHING from your old vCenter (RVTools is very handy here!)
Export EVERYTHING ELSE - (s)DRS Rules, VM Folders, Permissions (if necessary)
Export dvSwitch(es) PortGroups into a CSV
Create Standard vSwitch(es) on each Host.
Read in PortGoups and create them on each vSwitch. Choose a slightly different name. Mig-name is what I used.
Disconnect x NICs from dvSwitch. I only did half of mine at a time, just in case.
Create PortGroups on vSwitch on each Host that will be your VMKernels (VLANs).
Use Add-VirtualSwitchPhysicalNetworkAdapter. This moves VMNICs over and can turn a Portgroup into a VMKernel.
Change the PortGroup of the VMs from dvPortGroup to the new temporary PortGroups. Remember to do all of the VMs Adapters.
Move the rest of the VMNICs over.
Remove the Host from the dvSwitch.
Disconnect the ESX Host from the old vCenter.
Add ESX Host to new vCenter. Add it to the Datacenter, not a Cluster.
Move Host to proper Cluster.
Notes: Start:
PowerCLI of course!
Export – LucD’s site has the first two
End:
I pieced together ~5-10 PowerCLI scripts from across the Internets.
Heavily commented, in case you aren’t familiar with PowerShell or PowerCLI.

## Slide 8: Gotchas!
Do you have a “/” in your dvSwitch PortGroup names?
  In VCDB, entered as “%2f”.
  Screws up scripts & makes UI error out.
Make sure you check the VMware Compatibility Matrix!
  ESXi 5.0 Hosts can’t go into vCenter 6.5, only 6.0 and lower.
Are you using EVC Mode?
  DL360 Gen 9s do NOT like ESXi 5.0.
  A VM can vMotion on, but not off.
VCSA 6.5 backup/restore has an undocumented UI error.
  Restoring via SCP, needs a double forward slash after server name.
Notes: These are the oddities I have run into.
1 - Get rid of it.
If you don’t account for it, you end up outputting it, but then inputting it, which then gets input as the actual “%2f” value you received in your output.
Hooray for web encoding shenanigans!
  Get-VDSwitch/Get-VDPortGroup cmdlets return it.
  Get-VirtualPortGroup cmdlet does not return it.
2a - I got ahead of myself a bit.
2b – As I setup a swing vCenter, I now have no VUM to connect to.
3a - Only way to fix is to power off the VMs , move them, and then rebuild hosts.
  3b - For other working Hosts, I have no idea why, but it just worked out better that way. No errors.
  3c - This is how I found to move Hosts to the Datacenter, not the Cluster directly when adding Hosts.

## Slide 9: Contact!
Twitter/LinkedIn: @RichardKenyan
Email: rkenyan@gmail.com
I finally have GitHub setup!
https://github.com/richardkenyan
Thanks!
Richard Kenyan
vExpert 2018
BuffaloVMUG Co-Leader
Notes: Contact me:
…if you like me, and even if you don’t.
Programming;
I can put a puzzle together, but don’t ask me to create the puzzle pieces.